## Jira (5)
No. | Description | Acceptance Criteria | Feature | Story point | Priority | Assignee
US_01 | As a data engineer, I want the system to connect to APIs and ingest CSV data so that I can start the data extraction process. | - ETLState contains all required fields - Agent workflow executes in correct order - Retry mechanism works for failures - Audit logs capture all actions - Execution is deterministic | Data Ingestion | 55 | Highest | Meghana / Priya
US_02 | As a data engineer, I want the system to extract and transform data so that I can integrate multiple sources. | - {{read_csv()}} returns structured records - {{infer_schema()}} detects schema correctly - Raw data and schema stored in ETL state - Transformation pipeline executes successfully - Joins and merges are correct - Duplicate records are removed - Output data maintains schema consistency - Errors are logged properly | Data Processing & Mapping | 55 | Highest | Tenzing / Orges
US_03 | As a team lead, I want a coordination framework so that agents can collaborate and execute tasks reliably. | - ETLState structure includes all required fields (raw data, schema, plan, logs, etc.) - Agent workflow executes in defined sequence - System supports retry mechanisms for failed steps - Audit logs capture all agent actions - Pipeline execution is deterministic and reproducible - Agents communicate through shared state correctly | Agent Orchestration | 34 | Medium | Tenzing / Orges
US_04 | As a user, I want processed data to be stored and accessible so that I can query and analyze it. | - Data stored in SQLite successfully - Tables created/updated dynamically - API returns data in JSON format - Pagination works correctly - Schema inspection returns column details - Only read-only queries allowed - Unsafe queries are blocked | Data Storage & Access | 34 | Highest | Meghana / Priya
US_05 | As a user, I want to visualize and interact with my data so that I can understand results clearly. | - Drag & drop upload works - Dataset preview is displayed - ERD visualization is readable - Filters update data dynamically - UI displays processed data correctly - UI integrates with backend APIs | Data Visualization | 55 | Highest | Shreya / Kushawnth
US_06 | As a user, I want to monitor pipeline execution and agent decisions so that I understand how data is processed. | - Timeline shows sequence of operations - Each step displays agent name and action - Pipeline status (success/failure) visible - Execution stages displayed clearly - Timeline accessible in UI | Monitoring & Observability | 34 | Medium | Shreya / Kushawnth
US_07 | Allow users to upload CSV datasets into the system for processing. | - Row count and column count calculated - Column names and data types displayed - Null values detected - Schema validation works correctly - Validation errors shown clearly | Data Quality | 34 | Highest | Meghana/ Priya
US_08 | Enable users to upload data via drag & drop or provide API endpoints/links. | - Users can download data in CSV/JSON - Export works without errors - Downloaded data matches processed output - Export option visible in UI | Data Export | 21 | Lowest | Shreya / Kushawnth