## Jira (7)
No. | Description | Acceptance Criteria | Feature | Story points | Priority | Assignee
US_S2_01 | As a data steward, I want to validate and monitor data quality across the ETL pipeline so that errors are detected early and data integrity is maintained. | * ETL step execution logs are captured for each stage * Row-level errors are detected and clearly reported * Schema validation ensures input and output consistency * Null values and anomalies are identified correctly * Validation reports summarize all detected issues * API returns validation results in structured format * System prevents invalid data from progressing in pipeline | Data Validation & Quality | 55 | High | Tenzing / Orges
US_S2_02 | As a system, I want agents to coordinate and execute tasks in parallel so that ETL performance and scalability improve. | * ETLState contains all required shared fields * Agents execute tasks in correct workflow order * Parallel execution runs without data conflicts * Retry mechanism works correctly for failed steps * Agent logs capture execution details and decisions * Pipeline execution completes successfully under coordination * System handles partial failures without crashing entire flow | Multi-Agent System | 55 | Medium | Tenzing / Orges
US_S2_03 | As a user, I want flexible data ingestion methods so that I can easily upload datasets from multiple sources. | * File upload supports drag & drop functionality * API-based upload accepts valid file formats (CSV, JSON) * Upload progress is displayed to the user * Invalid files are rejected with clear error messages * Uploaded datasets are stored successfully * System handles large file uploads without failure | Data Input | 34 | High | Shreya / Kushawnth
US_S2_04 | As a user, I want to export processed data in multiple formats so that I can use it externally. | * Processed data can be exported in CSV format * Processed data can be exported in JSON format * Processed data can be exported in Excel format * Download API returns correct file response * Exported data maintains correct schema and formatting * System handles export errors gracefully | Data Output | 34 | High | Tenzing / Orges
US_S2_05 | As a user, I want to preview data before and after processing so that I understand transformations clearly. | * Dataset preview displays tabular data correctly * Schema view shows column names and data types * ERD visualization represents dataset relationships * Before and after data comparison is available * UI loads data efficiently without performance issues * API returns preview data accurately | Data Visualization | 34 | Medium | Shreya / Kushawnth
US_S2_06 | As a user, I want basic analytics and filtering tools so that I can quickly analyze datasets. | * System calculates average and median correctly * Summary statistics are generated for datasets * Backend supports filtering queries * Aggregation results are returned in structured format * Queries execute efficiently on large datasets * Errors are handled and reported clearly | Analytics | 34 | Medium | Tenzing / Orges
US_S2_07 | As a compliance officer, I want sensitive data to be redacted so that user privacy is protected. | *Schema changes are detected between pipeline runs *System identifies added, removed, or modified fields *Alerts are generated for unexpected schema changes *Schema change logs are stored for auditing *Monitoring integrates with ETL pipeline execution | Security | 21 | Medium | Tenzing / Orges